## Sheet1
Timeline
Task | Estimated Complete Date | Ownership | Status
Completing PoA | 2016-07-15 | Everyone | Done
Meeting Team and PoA | 2016-07-12 | Everyone | Done
Design First draft of UML | 2016-07-12 | Everyone | Done
Completing Draft PoA | 2016-07-14 | Everyone | Done
Completing Final PoA | 2016-07-15 | Everyone | Done
Creating Piece Class | 2016-07-15 | Everyone | In progress
King and Queen | 2016-07-15 | Amogh | In progress
Knight and Bishop | 2016-07-15 | Mo | In progress
Rook and Pawn | 2016-07-15 | Saad | In progress
Creating Board class | 2016-07-16 | Everyone | Not Started
ischeck() | 2016-07-16 | Amogh | Not Started
ischeckMate() | 2016-07-16 | Mo | Not Started
ischeckStaleMate() | 2016-07-16 | Saad | Not Started
Design Game Logic | 2016-07-17 | Mo | In progress
main.cc | 2016-07-16 | Mo | In progress
Resign, Move, Setup, and other game options | 2016-07-17 | Mo | Not Started
Calls to appropriate methods | 2016-07-17 | Mo | Not Started
Implementing View Class | 2016-07-18 | Amogh | Not Started
display board after initial configuration | 2016-07-18 | Amogh | Not Started
Creating Board/View Basic Text | 2016-07-18 | Saad | Not Started
Creating player and different levels | 2016-07-19 | Everyone | Not Started
Human | 2016-07-19 | Amogh | Not Started
Level 1 | 2016-07-19 | Mo | Not Started
Level 2 | 2016-07-19 | Saad | Not Started
Add Graphical Display | 2016-07-20 | Amogh | Not Started
Design Document and Final UML | 2016-07-21 | Everyone | In progress
Makeup day (Testing and Fixing Bugs) | 2016-07-21 | Everyone | Not Started
All bonus features listed in the assignment | 2016-07-21 | Everyone | Not Started